## Sheet1
SkillMatch AI System Gnatt Chart
Column1 | Tasks | Description | Start-Date | End-Date | Duration | Priority
| Project Requirement | Identify the problem we are trying to solve | 2026-05-01 | 2026-05-02 | 1 | Medium
| Define Scope | Level of Complexity and Abstraction | 2026-05-03 | 2026-05-06 | 3 | Medium
| Project Research | Carryout structured research about the project | 2026-05-07 | 2026-05-11 | 4 | Medium
| Planning | Based on the research, we come up with a plan to tackle the problem | 2026-05-12 | 2026-05-13 | 1 | High
| Plan Evaluation | Refine the plan if necessary | 2026-05-14 | 2026-05-15 | 1 | Medium
| System Design | High level and low level system design | 2026-05-16 | 2026-05-17 | 1 | Medium
| Tech Stack Review | Stack selection | 2026-05-17 | 2026-05-18 | 1 | Low
| UI Modeling | User experience design | 2026-05-18 | 2026-05-19 | 1 | Low
| AI model Selection | AI model approach selection | 2026-05-19 | 2026-05-20 | 1 | High
| Model Orchestration/Training | Fine tune the model | 2026-05-20 | 2026-05-22 | 2 | High
| Backend Development | Make the AI models accessible | 2026-05-23 | 2026-05-24 | 1 | Medium
| Backend Unit Testing | Carrout unit test on the AI components | 2026-05-24 | 2026-05-25 | 1 | Medium
| UI Development | Frontend development | 2026-05-25 | 2026-05-26 | 1 | High
| UI and Backend Intergration | Connect the Frontend to the AI system | 2026-05-26 | 2026-05-27 | 1 | High
| Testing | Carryout a series of tests | 2026-05-27 | 2026-05-28 | 1 | High
| Bug Reviews | Identify failures and fixs Proposition | 2026-05-28 | 2026-05-29 | 1 | High
| Launching | Launch the software | 2026-05-29 | 2026-05-30 | 1 | High
| Continuous Integration and Continuous | CICD | 2026-05-30 | 2026-09-15 | 108 | Low